## Commissioning_Resource_Schedule
Line Item | Role | Resource Name | Hourly Labor Rate | Labor Hours | Extended Labor Cost | Weekly Travel Cost | Total Travel Weeks | Extended Travel Cost | Total Extended Resource Cost | Start Week | End Week | Duration (Weeks) | Start Date Week Beginning | time axis 2025-12-14 to 2027-05-02
x | time axis 2025-12-14 to 2027-05-02
PLANNING, COORDINATION, & DOCUMENTATION | [86 empty] | x
| Management, Coordination, & Support | [85 empty] | x
| Cx Manager | Ben Solem | 185 | 3230 | 597550 | 2500 | 53 | 132500 | 730050 | 2025-12-14 | 2027-03-20 | 68 | 2025-12-15 | 50 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 30 | 50 | 50 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | [6 empty] | x
| Cx Scheduler/Coordinator | Lashica Woodard | 165 | 3130 | 516450 | 2500 | 32 | 80000 | 596450 | 2025-12-14 | 2027-03-06 | 66 | 2025-12-15 | 50 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 30 | 50 | 50 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | [8 empty] | x
| Doc Control-A | TBD | 110 | 3230 | 355300 | 2500 | 33 | 82500 | 437800 | 2025-12-14 | 2027-03-20 | 68 | 2025-12-15 | 50 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 30 | 50 | 50 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | [6 empty] | x
| Doc Control-B | TBD | 110 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 |  | 1 | 1899-12-31 | [73 empty] | x | bar: 2026-08-09 to 2027-05-02
| D2C Mech Engineering SME | Sherif Khamis | 185 | 260 | 48100 | 2500 | 0 | 0 | 48100 | 2025-12-14 | 2026-01-17 | 6 | 2025-12-15 | 2025-12-14: 50; 2025-12-21: 30; 2025-12-28: 30; 2026-01-04: 50; 2026-01-11: 50; 2026-01-18: 50
| Substation Elecrical Engineering SME | Daniel Dus | 185 | 260 | 48100 | 2500 | 0 | 0 | 48100 | 2025-12-14 | 2026-01-17 | 6 | 2025-12-15 | 2025-12-14: 50; 2025-12-21: 30; 2025-12-28: 30; 2026-01-04: 50; 2026-01-11: 50; 2026-01-18: 50
Planning Subtotal: |  |  |  | 10110 | 1565500 |  |  | 295000 | 1860500 | [77 empty] | x
x
SWITCHYARD & DATA HALL L2-L3 COMMISSIONING (CONCURRENT) | [86 empty] | x
| Switchyard - L2 Pre-Startup Inspections | [85 empty] | x
| Lead ECx-A | TBD | 150 | 550 | 82500 | 2500 | 11 | 27500 | 110000 | 2026-01-11 | 2026-03-21 | 12 | 2026-01-12 | 2026-01-11: 50; 2026-01-18: 50; 2026-01-25: 50; 2026-02-01: 50; 2026-02-08: 50; 2026-02-15: 50; 2026-02-22: 50; 2026-03-01: 50; 2026-03-08: 50; 2026-03-15: 50; 2026-03-22: 50 | x
| Lead ECx-B | TBD | 150 | 550 | 82500 | 2500 | 11 | 27500 | 110000 | 2026-01-11 | 2026-03-21 | 12 | 2026-01-12 | 2026-01-11: 50; 2026-01-18: 50; 2026-01-25: 50; 2026-02-01: 50; 2026-02-08: 50; 2026-02-15: 50; 2026-02-22: 50; 2026-03-01: 50; 2026-03-08: 50; 2026-03-15: 50; 2026-03-22: 50 | x
| ECx Tech-C | TBD | 120 | 550 | 66000 | 2500 | 11 | 27500 | 93500 | 2026-01-11 | 2026-03-21 | 12 | 2026-01-12 | 2026-01-11: 50; 2026-01-18: 50; 2026-01-25: 50; 2026-02-01: 50; 2026-02-08: 50; 2026-02-15: 50; 2026-02-22: 50; 2026-03-01: 50; 2026-03-08: 50; 2026-03-15: 50; 2026-03-22: 50 | x
| ECx Tech-D | TBD | 120 | 550 | 66000 | 2500 | 11 | 27500 | 93500 | 2026-01-11 | 2026-03-21 | 12 | 2026-01-12 | 2026-01-11: 50; 2026-01-18: 50; 2026-01-25: 50; 2026-02-01: 50; 2026-02-08: 50; 2026-02-15: 50; 2026-02-22: 50; 2026-03-01: 50; 2026-03-08: 50; 2026-03-15: 50; 2026-03-22: 50 | x
| Switchyard - L3 Startup & Energization | [85 empty] | x
| Lead ECx-A | TBD | 150 | 250 | 37500 | 2500 | 5 | 12500 | 50000 | 2026-03-29 | 2026-04-25 | 6 | 2026-03-30 | 2026-03-29: 50; 2026-04-05: 50; 2026-04-12: 50; 2026-04-19: 50; 2026-04-26: 50 | x
| Lead ECx-B | TBD | 150 | 250 | 37500 | 2500 | 5 | 12500 | 50000 | 2026-03-29 | 2026-04-25 | 6 | 2026-03-30 | 2026-03-29: 50; 2026-04-05: 50; 2026-04-12: 50; 2026-04-19: 50; 2026-04-26: 50 | x
| ECx Tech-C | TBD | 120 | 250 | 30000 | 2500 | 5 | 12500 | 42500 | 2026-03-29 | 2026-04-25 | 6 | 2026-03-30 | 2026-03-29: 50; 2026-04-05: 50; 2026-04-12: 50; 2026-04-19: 50; 2026-04-26: 50 | x
| ECx Tech-D | TBD | 120 | 250 | 30000 | 2500 | 5 | 12500 | 42500 | 2026-03-29 | 2026-04-25 | 6 | 2026-03-30 | 2026-03-29: 50; 2026-04-05: 50; 2026-04-12: 50; 2026-04-19: 50; 2026-04-26: 50 | x
Switchyard L2-L3 Subtotal |  |  |  | 3200 | 432000 |  |  | 160000 | 592000 | [77 empty] | x
x
SWITCHYARD - L4-L5 TESTING | [86 empty] | x
| Switchyard - L4 Functional Testing | [85 empty] | x
| Lead ECx-A | TBD | 150 | 440 | 66000 | 2500 | 9 | 22500 | 88500 | 2026-05-03 | 2026-06-27 | 10 | 2026-05-04 | 2026-05-03: 40; 2026-05-10: 50; 2026-05-17: 50; 2026-05-24: 50; 2026-05-31: 50; 2026-06-07: 50; 2026-06-14: 50; 2026-06-21: 50; 2026-06-28: 50 | x
| Lead ECx-B | TBD | 150 | 440 | 66000 | 2500 | 9 | 22500 | 88500 | 2026-05-03 | 2026-06-27 | 10 | 2026-05-04 | 2026-05-03: 40; 2026-05-10: 50; 2026-05-17: 50; 2026-05-24: 50; 2026-05-31: 50; 2026-06-07: 50; 2026-06-14: 50; 2026-06-21: 50; 2026-06-28: 50 | x
| ECx Tech-C | TBD | 120 | 440 | 52800 | 2500 | 9 | 22500 | 75300 | 2026-05-03 | 2026-06-27 | 10 | 2026-05-04 | 2026-05-03: 40; 2026-05-10: 50; 2026-05-17: 50; 2026-05-24: 50; 2026-05-31: 50; 2026-06-07: 50; 2026-06-14: 50; 2026-06-21: 50; 2026-06-28: 50 | x
| ECx Tech-D | TBD | 120 | 440 | 52800 | 2500 | 9 | 22500 | 75300 | 2026-05-03 | 2026-06-27 | 10 | 2026-05-04 | 2026-05-03: 40; 2026-05-10: 50; 2026-05-17: 50; 2026-05-24: 50; 2026-05-31: 50; 2026-06-07: 50; 2026-06-14: 50; 2026-06-21: 50; 2026-06-28: 50 | x
| Switchyard - L5 IST | [85 empty] | x
| Lead ECx-A | TBD | 150 | 190 | 28500 | 2500 | 4 | 10000 | 38500 | 2026-07-05 | 2026-07-25 | 5 | 2026-07-06 | 2026-07-05: 40; 2026-07-12: 50; 2026-07-19: 50; 2026-07-26: 50 | x
| Lead ECx-B | TBD | 150 | 140 | 21000 | 2500 | 3 | 7500 | 28500 | 2026-07-05 | 2026-07-18 | 4 | 2026-07-06 | 2026-07-05: 40; 2026-07-12: 50; 2026-07-19: 50 | x
| ECx Tech-C | TBD | 120 | 190 | 22800 | 2500 | 4 | 10000 | 32800 | 2026-07-05 | 2026-07-25 | 5 | 2026-07-06 | 2026-07-05: 40; 2026-07-12: 50; 2026-07-19: 50; 2026-07-26: 50 | x
| ECx Tech-D | TBD | 120 | 190 | 22800 | 2500 | 4 | 10000 | 32800 | 2026-07-05 | 2026-07-25 | 5 | 2026-07-06 | 2026-07-05: 40; 2026-07-12: 50; 2026-07-19: 50; 2026-07-26: 50 | x
Switchyard L4-L5 Subtotal |  |  |  | 2470 | 332700 |  |  | 127500 | 460200 | [77 empty] | x
Switchyard Subtotal |  |  |  | 5670 | 1196700 |  |  | 447500 | 1644200 | [77 empty] | x
x
| Data Halls Ph 1-6 - L2 Pre-Startup Inspections (Concurrent) | [85 empty] | x
| Lead ECx-C | TBD | 150 | 1730 | 259500 | 2500 | 35 | 87500 | 347000 | 2026-01-11 | 2026-09-05 | 36 | 2026-01-12 | 2026-01-11: 50; 2026-01-18: 50; 2026-01-25: 50; 2026-02-01: 50; 2026-02-08: 50; 2026-02-15: 50; 2026-02-22: 50; 2026-03-01: 50; 2026-03-08: 50; 2026-03-15: 50; 2026-03-22: 50; 2026-03-29: 50; 2026-04-05: 50; 2026-04-12: 50; 2026-04-19: 50; 2026-04-26: 50; 2026-05-03: 40; 2026-05-10: 50; 2026-05-17: 50; 2026-05-24: 50; 2026-05-31: 50; 2026-06-07: 50; 2026-06-14: 50; 2026-06-21: 50; 2026-06-28: 50; 2026-07-05: 40; 2026-07-12: 50; 2026-07-19: 50; 2026-07-26: 50; 2026-08-02: 50; 2026-08-09: 50; 2026-08-16: 50; 2026-08-23: 50; 2026-08-30: 50; 2026-09-06: 50 | x
| Lead ECx-A | TBD | 150 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 |  | 1 | 1899-12-31 | [73 empty] | x | bar: 2026-08-09 to 2027-05-02
| ECx Tech-B | TBD | 120 | 1380 | 165600 | 2500 | 28 | 70000 | 235600 | 2026-01-11 | 2026-07-18 | 29 | 2026-01-12 | 2026-01-11: 50; 2026-01-18: 50; 2026-01-25: 50; 2026-02-01: 50; 2026-02-08: 50; 2026-02-15: 50; 2026-02-22: 50; 2026-03-01: 50; 2026-03-08: 50; 2026-03-15: 50; 2026-03-22: 50; 2026-03-29: 50; 2026-04-05: 50; 2026-04-12: 50; 2026-04-19: 50; 2026-04-26: 50; 2026-05-03: 40; 2026-05-10: 50; 2026-05-17: 50; 2026-05-24: 50; 2026-05-31: 50; 2026-06-07: 50; 2026-06-14: 50; 2026-06-21: 50; 2026-06-28: 50; 2026-07-05: 40; 2026-07-12: 50; 2026-07-19: 50 | x
| Lead MCx-A | TBD | 150 | 1680 | 252000 | 2500 | 34 | 85000 | 337000 | 2026-01-11 | 2026-08-29 | 34 | 2026-01-12 | 2026-01-11: 50; 2026-01-18: 50; 2026-01-25: 50; 2026-02-01: 50; 2026-02-08: 50; 2026-02-15: 50; 2026-02-22: 50; 2026-03-01: 50; 2026-03-08: 50; 2026-03-15: 50; 2026-03-22: 50; 2026-03-29: 50; 2026-04-05: 50; 2026-04-12: 50; 2026-04-19: 50; 2026-04-26: 50; 2026-05-03: 40; 2026-05-10: 50; 2026-05-17: 50; 2026-05-24: 50; 2026-05-31: 50; 2026-06-07: 50; 2026-06-14: 50; 2026-06-21: 50; 2026-06-28: 50; 2026-07-05: 40; 2026-07-12: 50; 2026-07-19: 50; 2026-07-26: 50; 2026-08-02: 50; 2026-08-09: 50; 2026-08-16: 50; 2026-08-23: 50; 2026-08-30: 50
| MCx Tech-A | TBD | 120 | 1680 | 201600 | 2500 | 34 | 85000 | 286600 | 2026-01-11 | 2026-08-29 | 35 | 2026-01-12 | 2026-01-11: 50; 2026-01-18: 50; 2026-01-25: 50; 2026-02-01: 50; 2026-02-08: 50; 2026-02-15: 50; 2026-02-22: 50; 2026-03-01: 50; 2026-03-08: 50; 2026-03-15: 50; 2026-03-22: 50; 2026-03-29: 50; 2026-04-05: 50; 2026-04-12: 50; 2026-04-19: 50; 2026-04-26: 50; 2026-05-03: 40; 2026-05-10: 50; 2026-05-17: 50; 2026-05-24: 50; 2026-05-31: 50; 2026-06-07: 50; 2026-06-14: 50; 2026-06-21: 50; 2026-06-28: 50; 2026-07-05: 40; 2026-07-12: 50; 2026-07-19: 50; 2026-07-26: 50; 2026-08-02: 50; 2026-08-09: 50; 2026-08-16: 50; 2026-08-23: 50; 2026-08-30: 50 | x
| MCx Tech-B | TBD | 120 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 |  | 1 | 1899-12-31 | [73 empty] | x | bar: 2026-08-09 to 2027-05-02
| Data Halls Ph 1-6 - L3 Startup & Energization (Concurrent) | [85 empty] | x
| Lead ECx-D | TBD | 150 | 2060 | 309000 | 2500 | 42 | 105000 | 414000 | 2026-03-01 | 2026-12-12 | 42 | 2026-03-02 | 2026-03-01: 50; 2026-03-08: 50; 2026-03-15: 50; 2026-03-22: 50; 2026-03-29: 50; 2026-04-05: 50; 2026-04-12: 50; 2026-04-19: 50; 2026-04-26: 50; 2026-05-03: 40; 2026-05-10: 50; 2026-05-17: 50; 2026-05-24: 50; 2026-05-31: 50; 2026-06-07: 50; 2026-06-14: 50; 2026-06-21: 50; 2026-06-28: 50; 2026-07-05: 40; 2026-07-12: 50; 2026-07-19: 50; 2026-07-26: 50; 2026-08-02: 50; 2026-08-09: 50; 2026-08-16: 50; 2026-08-23: 50; 2026-08-30: 50; 2026-09-06: 50; 2026-09-13: 50; 2026-09-20: 50; 2026-09-27: 50; 2026-10-04: 50; 2026-10-11: 50; 2026-10-18: 50; 2026-10-25: 50; 2026-11-01: 50; 2026-11-08: 50; 2026-11-15: 50; 2026-11-22: 50; 2026-11-29: 30; 2026-12-06: 50; 2026-12-13: 50
| ECx Tech-C | TBD | 120 | 0 | 0 | 2500 | 0 | 0 | 0 |  |  | 0 | bar: 2025-12-14 to 2026-04-26; 2026-08-09 to 2027-05-02
| ECx Tech-D | TBD | 120 | 0 | 0 | 2500 | 0 | 0 | 0 |  |  | 0 | bar: 2025-12-14 to 2026-04-26; 2026-08-09 to 2027-05-02
| Lead ECx-B | TBD | 150 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 |  | 1 | 1899-12-31 | [73 empty] | x | bar: 2026-08-09 to 2027-05-02
| ECx Tech-A | TBD | 120 | 1330 | 159600 | 2500 | 27 | 67500 | 227100 | 2026-03-01 | 2026-08-29 | 28 | 2026-03-02 | 2026-03-01: 50; 2026-03-08: 50; 2026-03-15: 50; 2026-03-22: 50; 2026-03-29: 50; 2026-04-05: 50; 2026-04-12: 50; 2026-04-19: 50; 2026-04-26: 50; 2026-05-03: 40; 2026-05-10: 50; 2026-05-17: 50; 2026-05-24: 50; 2026-05-31: 50; 2026-06-07: 50; 2026-06-14: 50; 2026-06-21: 50; 2026-06-28: 50; 2026-07-05: 40; 2026-07-12: 50; 2026-07-19: 50; 2026-07-26: 50; 2026-08-02: 50; 2026-08-09: 50; 2026-08-16: 50; 2026-08-23: 50; 2026-08-30: 50 | x
| Lead MCx-C | TBD | 150 | 2010 | 301500 | 2500 | 41 | 102500 | 404000 | 2026-03-01 | 2026-12-05 | 42 | 2026-03-02 | 2026-03-01: 50; 2026-03-08: 50; 2026-03-15: 50; 2026-03-22: 50; 2026-03-29: 50; 2026-04-05: 50; 2026-04-12: 50; 2026-04-19: 50; 2026-04-26: 50; 2026-05-03: 40; 2026-05-10: 50; 2026-05-17: 50; 2026-05-24: 50; 2026-05-31: 50; 2026-06-07: 50; 2026-06-14: 50; 2026-06-21: 50; 2026-06-28: 50; 2026-07-05: 40; 2026-07-12: 50; 2026-07-19: 50; 2026-07-26: 50; 2026-08-02: 50; 2026-08-09: 50; 2026-08-16: 50; 2026-08-23: 50; 2026-08-30: 50; 2026-09-06: 50; 2026-09-13: 50; 2026-09-20: 50; 2026-09-27: 50; 2026-10-04: 50; 2026-10-11: 50; 2026-10-18: 50; 2026-10-25: 50; 2026-11-01: 50; 2026-11-08: 50; 2026-11-15: 50; 2026-11-22: 50; 2026-11-29: 30; 2026-12-06: 50 | x
| Lead MCx-D | TBD | 150 | 1960 | 294000 | 2500 | 40 | 100000 | 394000 | 2026-03-01 | 2026-11-28 | 40 | 2026-03-02 | 2026-03-01: 50; 2026-03-08: 50; 2026-03-15: 50; 2026-03-22: 50; 2026-03-29: 50; 2026-04-05: 50; 2026-04-12: 50; 2026-04-19: 50; 2026-04-26: 50; 2026-05-03: 40; 2026-05-10: 50; 2026-05-17: 50; 2026-05-24: 50; 2026-05-31: 50; 2026-06-07: 50; 2026-06-14: 50; 2026-06-21: 50; 2026-06-28: 50; 2026-07-05: 40; 2026-07-12: 50; 2026-07-19: 50; 2026-07-26: 50; 2026-08-02: 50; 2026-08-09: 50; 2026-08-16: 50; 2026-08-23: 50; 2026-08-30: 50; 2026-09-06: 50; 2026-09-13: 50; 2026-09-20: 50; 2026-09-27: 50; 2026-10-04: 50; 2026-10-11: 50; 2026-10-18: 50; 2026-10-25: 50; 2026-11-01: 50; 2026-11-08: 50; 2026-11-15: 50; 2026-11-22: 50; 2026-11-29: 30
| MCx Tech-C | TBD | 120 | 0 | 0 | 2500 | 0 | 0 | 0 |  |  | 0 | bar: 2025-12-14 to 2026-04-26; 2026-08-09 to 2027-05-02
| MCx Tech-D | TBD | 120 | 0 | 0 | 2500 | 0 | 0 | 0 |  |  | 0 | bar: 2025-12-14 to 2026-04-26; 2026-08-09 to 2027-05-02
| Lead MCx-B | TBD | 150 | 0 | 0 | 2500 | 0 | 0 | 0 |  |  | 0 | bar: 2025-12-14 to 2026-04-26; 2026-08-09 to 2027-05-02
| MCx Tech-B | TBD | 120 | 0 | 0 | 2500 | 0 | 0 | 0 | 0 |  | 1 | 1899-12-31 | [73 empty] | x | bar: 2026-08-09 to 2027-05-02
Data Hall L2-L3 |  |  |  | 13830 | 1942800 |  |  | 702500 | 2645300 | [77 empty] | x
x
PHASE 1 - DATA HALL | [86 empty] | x
| Phase 1 - L4 Functional Testing (4 weeks) | [85 empty] | x
| Lead ECx-B | TBD | 150 | 250 | 37500 | 2500 | 5 | 12500 | 50000 | 2026-07-26 | 2026-08-22 | 6 | 2026-07-27 | 2026-07-26: 50; 2026-08-02: 50; 2026-08-09: 50; 2026-08-16: 50; 2026-08-23: 50 | x
| ECx Tech-B | TBD | 120 | 250 | 30000 | 2500 | 5 | 12500 | 42500 | 2026-07-26 | 2026-08-22 | 6 | 2026-07-27 | 2026-07-26: 50; 2026-08-02: 50; 2026-08-09: 50; 2026-08-16: 50; 2026-08-23: 50 | x
| ECx Tech-D | TBD | 120 | 200 | 24000 | 2500 | 4 | 10000 | 34000 | 2026-08-02 | 2026-08-22 | 5 | 2026-08-03 | 2026-08-02: 50; 2026-08-09: 50; 2026-08-16: 50; 2026-08-23: 50 | x
| Lead MCx-B | TBD | 150 | 250 | 37500 | 2500 | 5 | 12500 | 50000 | 2026-07-26 | 2026-08-22 | 6 | 2026-07-27 | 2026-07-26: 50; 2026-08-02: 50; 2026-08-09: 50; 2026-08-16: 50; 2026-08-23: 50 | x
| MCx Tech-B | TBD | 120 | 250 | 30000 | 2500 | 5 | 12500 | 42500 | 2026-07-26 | 2026-08-22 | 6 | 2026-07-27 | 2026-07-26: 50; 2026-08-02: 50; 2026-08-09: 50; 2026-08-16: 50; 2026-08-23: 50 | x
| MCx Tech-D | TBD | 120 | 250 | 30000 | 2502 | 5 | 12510 | 42510 | 2026-07-26 | 2026-08-22 | 6 | 2026-07-27 | 2026-07-26: 50; 2026-08-02: 50; 2026-08-09: 50; 2026-08-16: 50; 2026-08-23: 50 | x
| Phase 1 - L5 IST (2 weeks) | [85 empty] | x
| Lead ECx-B | TBD | 150 | 100 | 15000 | 2500 | 2 | 5000 | 20000 | 2026-08-30 | 2026-09-05 | 3 | 2026-08-31 | 2026-08-30: 50; 2026-09-06: 50 | x
| ECx Tech-B | TBD | 120 | 100 | 12000 | 2500 | 2 | 5000 | 17000 | 2026-08-30 | 2026-09-05 | 3 | 2026-08-31 | 2026-08-30: 50; 2026-09-06: 50 | x
| ECx Tech-D | TBD | 120 | 100 | 12000 | 2500 | 2 | 5000 | 17000 | 2026-08-30 | 2026-09-05 | 3 | 2026-08-31 | 2026-08-30: 50; 2026-09-06: 50 | x
| Lead MCx-B | TBD | 150 | 100 | 15000 | 2500 | 2 | 5000 | 20000 | 2026-08-30 | 2026-09-05 | 3 | 2026-08-31 | 2026-08-30: 50; 2026-09-06: 50 | x
| MCx Tech-B | TBD | 120 | 100 | 12000 | 2500 | 2 | 5000 | 17000 | 2026-08-30 | 2026-09-05 | 3 | 2026-08-31 | 2026-08-30: 50; 2026-09-06: 50 | x
| MCx Tech-D | TBD | 120 | 100 | 12000 | 2502 | 2 | 5004 | 17004 | 2026-08-30 | 2026-09-05 | 3 | 2026-08-31 | 2026-08-30: 50; 2026-09-06: 50 | x
Phase 1 - Data Halls & Network L4-L5 |  |  |  | 2050 | 267000 |  |  | 102514 | 369514 | [77 empty] | x
x
PHASE 2 - DATA HALL | [86 empty] | x
| Phase 2 - L4 Functional Testing (4 weeks) | [85 empty] | x
| Lead ECx-A | TBD | 150 | 200 | 30000 | 2500 | 4 | 10000 | 40000 | 2026-09-13 | 2026-10-03 | 5 | 2026-09-14 | 2026-09-13: 50; 2026-09-20: 50; 2026-09-27: 50; 2026-10-04: 50 | x
| ECx Tech-A | TBD | 120 | 250 | 30000 | 2500 | 5 | 12500 | 42500 | 2026-09-06 | 2026-10-03 | 6 | 2026-09-07 | 2026-09-06: 50; 2026-09-13: 50; 2026-09-20: 50; 2026-09-27: 50; 2026-10-04: 50 | x
| ECx Tech-C | TBD | 120 | 250 | 30000 | 2500 | 5 | 12500 | 42500 | 2026-09-06 | 2026-10-03 | 6 | 2026-09-07 | 2026-09-06: 50; 2026-09-13: 50; 2026-09-20: 50; 2026-09-27: 50; 2026-10-04: 50 | x
| Lead MCx-A | TBD | 150 | 250 | 37500 | 2500 | 5 | 12500 | 50000 | 2026-09-06 | 2026-10-03 | 6 | 2026-09-07 | 2026-09-06: 50; 2026-09-13: 50; 2026-09-20: 50; 2026-09-27: 50; 2026-10-04: 50 | x
| MCx Tech-A | TBD | 120 | 250 | 30000 | 2500 | 5 | 12500 | 42500 | 2026-09-06 | 2026-10-03 | 6 | 2026-09-07 | 2026-09-06: 50; 2026-09-13: 50; 2026-09-20: 50; 2026-09-27: 50; 2026-10-04: 50 | x
| MCx Tech-C | TBD | 120 | 250 | 30000 | 2500 | 5 | 12500 | 42500 | 2026-09-06 | 2026-10-03 | 6 | 2026-09-07 | 2026-09-06: 50; 2026-09-13: 50; 2026-09-20: 50; 2026-09-27: 50; 2026-10-04: 50 | x
| Phase 2 - L5 IST (2 weeks) | [85 empty] | x
| Lead ECx-A | TBD | 150 | 100 | 15000 | 2500 | 2 | 5000 | 20000 | 2026-10-11 | 2026-10-17 | 3 | 2026-10-12 | 2026-10-11: 50; 2026-10-18: 50 | x
| ECx Tech-A | TBD | 120 | 100 | 12000 | 2500 | 2 | 5000 | 17000 | 2026-10-11 | 2026-10-17 | 3 | 2026-10-12 | 2026-10-11: 50; 2026-10-18: 50 | x
| ECx Tech-C | TBD | 120 | 100 | 12000 | 2500 | 2 | 5000 | 17000 | 2026-10-11 | 2026-10-17 | 3 | 2026-10-12 | 2026-10-11: 50; 2026-10-18: 50 | x
| Lead MCx-A | TBD | 150 | 100 | 15000 | 2500 | 2 | 5000 | 20000 | 2026-10-11 | 2026-10-17 | 3 | 2026-10-12 | 2026-10-11: 50; 2026-10-18: 50 | x
| MCx Tech-A | TBD | 120 | 100 | 12000 | 2500 | 2 | 5000 | 17000 | 2026-10-11 | 2026-10-17 | 3 | 2026-10-12 | 2026-10-11: 50; 2026-10-18: 50 | x
| MCx Tech-C | TBD | 120 | 100 | 12000 | 2500 | 2 | 5000 | 17000 | 2026-10-11 | 2026-10-17 | 3 | 2026-10-12 | 2026-10-11: 50; 2026-10-18: 50 | x
Phase 2 - Data Halls L4-L5 |  |  |  | 2050 | 265500 |  |  | 102500 | 368000 | [77 empty] | x
x
PHASE 3 - DATA HALL | [86 empty] | x
| Phase 3 - L4 Functional Testing (3 weeks) | [85 empty] | x
| Lead ECx-B | TBD | 150 | 200 | 30000 | 2500 | 4 | 10000 | 40000 | 2026-10-18 | 2026-11-07 | 5 | 2026-10-19 | 2026-10-18: 50; 2026-10-25: 50; 2026-11-01: 50; 2026-11-08: 50 | x
| ECx Tech-B | TBD | 120 | 200 | 24000 | 2500 | 4 | 10000 | 34000 | 2026-10-18 | 2026-11-07 | 5 | 2026-10-19 | 2026-10-18: 50; 2026-10-25: 50; 2026-11-01: 50; 2026-11-08: 50 | x
| ECx Tech-D | TBD | 120 | 200 | 24000 | 2500 | 4 | 10000 | 34000 | 2026-10-18 | 2026-11-07 | 5 | 2026-10-19 | 2026-10-18: 50; 2026-10-25: 50; 2026-11-01: 50; 2026-11-08: 50 | x
| Lead MCx-B | TBD | 150 | 200 | 30000 | 2500 | 4 | 10000 | 40000 | 2026-10-18 | 2026-11-07 | 5 | 2026-10-19 | 2026-10-18: 50; 2026-10-25: 50; 2026-11-01: 50; 2026-11-08: 50 | x
| MCx Tech-B | TBD | 120 | 200 | 24000 | 2500 | 4 | 10000 | 34000 | 2026-10-18 | 2026-11-07 | 5 | 2026-10-19 | 2026-10-18: 50; 2026-10-25: 50; 2026-11-01: 50; 2026-11-08: 50 | x
| MCx Tech-D | TBD | 120 | 200 | 24000 | 2500 | 4 | 10000 | 34000 | 2026-10-18 | 2026-11-07 | 5 | 2026-10-19 | 2026-10-18: 50; 2026-10-25: 50; 2026-11-01: 50; 2026-11-08: 50 | x
| Phase 3 - L5 IST (2 weeks) | [85 empty] | x
| Lead ECx-B | TBD | 150 | 100 | 15000 | 2500 | 2 | 5000 | 20000 | 2026-11-15 | 2026-11-21 | 3 | 2026-11-16 | 2026-11-15: 50; 2026-11-22: 50 | x
| ECx Tech-B | TBD | 120 | 100 | 12000 | 2500 | 2 | 5000 | 17000 | 2026-11-15 | 2026-11-21 | 3 | 2026-11-16 | 2026-11-15: 50; 2026-11-22: 50 | x
| ECx Tech-D | TBD | 120 | 100 | 12000 | 2500 | 2 | 5000 | 17000 | 2026-11-15 | 2026-11-21 | 3 | 2026-11-16 | 2026-11-15: 50; 2026-11-22: 50 | x
| Lead MCx-B | TBD | 150 | 100 | 15000 | 2500 | 2 | 5000 | 20000 | 2026-11-15 | 2026-11-21 | 3 | 2026-11-16 | 2026-11-15: 50; 2026-11-22: 50 | x
| MCx Tech-B | TBD | 120 | 100 | 12000 | 2500 | 2 | 5000 | 17000 | 2026-11-15 | 2026-11-21 | 3 | 2026-11-16 | 2026-11-15: 50; 2026-11-22: 50 | x
| MCx Tech-D | TBD | 120 | 100 | 12000 | 2502 | 2 | 5004 | 17004 | 2026-11-15 | 2026-11-21 | 3 | 2026-11-16 | 2026-11-15: 50; 2026-11-22: 50 | x
Phase 3 - Data Halls L4-L5 |  |  |  | 1800 | 234000 |  |  | 90004 | 324004 | [77 empty] | x
x
PHASE 4 - DATA HALL | [86 empty] | x
| Phase 4 - L4 Functional Testing (4 weeks - Thanksgiving) | [85 empty] | x
| Lead ECx-A | TBD | 150 | 210 | 31500 | 2500 | 5 | 12500 | 44000 | 2026-11-22 | 2026-12-19 | 6 | 2026-11-23 | 2026-11-22: 50; 2026-11-29: 30; 2026-12-06: 50; 2026-12-13: 50; 2026-12-20: 30 | x
| ECx Tech-A | TBD | 120 | 210 | 25200 | 2500 | 5 | 12500 | 37700 | 2026-11-22 | 2026-12-19 | 6 | 2026-11-23 | 2026-11-22: 50; 2026-11-29: 30; 2026-12-06: 50; 2026-12-13: 50; 2026-12-20: 30 | x
| ECx Tech-C | TBD | 120 | 210 | 25200 | 2500 | 5 | 12500 | 37700 | 2026-11-22 | 2026-12-19 | 6 | 2026-11-23 | 2026-11-22: 50; 2026-11-29: 30; 2026-12-06: 50; 2026-12-13: 50; 2026-12-20: 30 | x
| Lead MCx-A | TBD | 150 | 210 | 31500 | 2500 | 5 | 12500 | 44000 | 2026-11-22 | 2026-12-19 | 6 | 2026-11-23 | 2026-11-22: 50; 2026-11-29: 30; 2026-12-06: 50; 2026-12-13: 50; 2026-12-20: 30 | x
| MCx Tech-A | TBD | 120 | 210 | 25200 | 2501 | 5 | 12505 | 37705 | 2026-11-22 | 2026-12-19 | 6 | 2026-11-23 | 2026-11-22: 50; 2026-11-29: 30; 2026-12-06: 50; 2026-12-13: 50; 2026-12-20: 30 | x
| MCx Tech-C | TBD | 120 | 160 | 19200 | 2502 | 4 | 10008 | 29208 | 2026-11-29 | 2026-12-19 | 5 | 2026-11-30 | 2026-11-29: 30; 2026-12-06: 50; 2026-12-13: 50; 2026-12-20: 30 | x
| MCx Tech-D | TBD | 120 | 160 | 19200 | 2502 | 4 | 10008 | 29208 | 2026-11-29 | 2026-12-19 | 5 | 2026-11-30 | 2026-11-29: 30; 2026-12-06: 50; 2026-12-13: 50; 2026-12-20: 30 | x
| Phase 4 - L5 IST (3 weeks - Christmas) | [85 empty] | x
| Lead ECx-A | TBD | 150 | 80 | 12000 | 2500 | 2 | 5000 | 17000 | 2026-12-27 | 2027-01-02 | 3 | 2026-12-28 | 2026-12-27: 30; 2027-01-03: 50 | x
| ECx Tech-A | TBD | 120 | 80 | 9600 | 2500 | 2 | 5000 | 14600 | 2026-12-27 | 2027-01-02 | 3 | 2026-12-28 | 2026-12-27: 30; 2027-01-03: 50 | x
| ECx Tech-C | TBD | 120 | 80 | 9600 | 2500 | 2 | 5000 | 14600 | 2026-12-27 | 2027-01-02 | 3 | 2026-12-28 | 2026-12-27: 30; 2027-01-03: 50 | x
| Lead MCx-A | TBD | 150 | 80 | 12000 | 2500 | 2 | 5000 | 17000 | 2026-12-27 | 2027-01-02 | 3 | 2026-12-28 | 2026-12-27: 30; 2027-01-03: 50 | x
| MCx Tech-A |  | 120 | 80 | 9600 | 2501 | 2 | 5002 | 14602 | 2026-12-27 | 2027-01-02 | 3 | 2026-12-28 | 2026-12-27: 30; 2027-01-03: 50 | x
| MCx Tech-C |  | 120 | 80 | 9600 | 2502 | 2 | 5004 | 14604 | 2026-12-27 | 2027-01-02 | 3 | 2026-12-28 | 2026-12-27: 30; 2027-01-03: 50 | x
| MCx Tech-D | TBD | 120 | 80 | 9600 | 2502 | 2 | 5004 | 14604 | 2026-12-27 | 2027-01-02 | 3 | 2026-12-28 | 2026-12-27: 30; 2027-01-03: 50 | x
Phase 4 - Data Halls L4-L5 |  |  |  | 1850 | 239400 |  |  | 112527 | 351927 | [77 empty] | x
x
PHASE 5 - DATA HALL | [86 empty] | x
| Phase 5 - L4 Functional Testing (3 weeks) | [85 empty] | x
| Lead ECx-B | TBD | 150 | 200 | 30000 | 2500 | 4 | 10000 | 40000 | 2027-01-03 | 2027-01-23 | 5 | 2027-01-04 | 2027-01-03: 50; 2027-01-10: 50; 2027-01-17: 50; 2027-01-24: 50 | x
| ECx Tech-B | TBD | 120 | 200 | 24000 | 2500 | 4 | 10000 | 34000 | 2027-01-03 | 2027-01-23 | 5 | 2027-01-04 | 2027-01-03: 50; 2027-01-10: 50; 2027-01-17: 50; 2027-01-24: 50 | x
| ECx Tech-D | TBD | 120 | 200 | 24000 | 2501 | 4 | 10004 | 34004 | 2027-01-03 | 2027-01-23 | 5 | 2027-01-04 | 2027-01-03: 50; 2027-01-10: 50; 2027-01-17: 50; 2027-01-24: 50 | x
| Lead MCx-B | TBD | 150 | 200 | 30000 | 2500 | 4 | 10000 | 40000 | 2027-01-03 | 2027-01-23 | 5 | 2027-01-04 | 2027-01-03: 50; 2027-01-10: 50; 2027-01-17: 50; 2027-01-24: 50 | x
| MCx Tech-B | TBD | 120 | 200 | 24000 | 2500 | 4 | 10000 | 34000 | 2027-01-03 | 2027-01-23 | 5 | 2027-01-04 | 2027-01-03: 50; 2027-01-10: 50; 2027-01-17: 50; 2027-01-24: 50 | x
| MCx Tech-D | TBD | 120 | 150 | 18000 | 2502 | 3 | 7506 | 25506 | 2027-01-10 | 2027-01-23 | 4 | 2027-01-11 | 2027-01-10: 50; 2027-01-17: 50; 2027-01-24: 50 | x
| Phase 5 - L5 IST (2 Weeks) | [85 empty] | x
| Lead ECx-B | TBD | 150 | 100 | 15000 | 2500 | 2 | 5000 | 20000 | 2027-01-31 | 2027-02-06 | 3 | 2027-02-01 | 2027-01-31: 50; 2027-02-07: 50 | x
| ECx Tech-B | TBD | 120 | 100 | 12000 | 2500 | 2 | 5000 | 17000 | 2027-01-31 | 2027-02-06 | 3 | 2027-02-01 | 2027-01-31: 50; 2027-02-07: 50 | x
| ECx Tech-D | TBD | 120 | 100 | 12000 | 2501 | 2 | 5002 | 17002 | 2027-01-31 | 2027-02-06 | 3 | 2027-02-01 | 2027-01-31: 50; 2027-02-07: 50 | x
| Lead MCx-B | TBD | 150 | 100 | 15000 | 2500 | 2 | 5000 | 20000 | 2027-01-31 | 2027-02-06 | 3 | 2027-02-01 | 2027-01-31: 50; 2027-02-07: 50 | x
| MCx Tech-B | TBD | 120 | 100 | 12000 | 2500 | 2 | 5000 | 17000 | 2027-01-31 | 2027-02-06 | 3 | 2027-02-01 | 2027-01-31: 50; 2027-02-07: 50 | x
| MCx Tech-D | TBD | 120 | 100 | 12000 | 2502 | 2 | 5004 | 17004 | 2027-01-31 | 2027-02-06 | 3 | 2027-02-01 | 2027-01-31: 50; 2027-02-07: 50 | x
Phase 5 - Data Halls L4-L5 |  |  |  | 1750 | 228000 |  |  | 87516 | 315516 | [77 empty] | x
x
PHASE 6 - DATA HALL | [86 empty] | x
| Phase 6 - L4 Functional Testing (3 weeks) | [85 empty] | x
| Lead ECx-A | TBD | 150 | 200 | 30000 | 2500 | 4 | 10000 | 40000 | 2027-02-07 | 2027-02-27 | 5 | 2027-02-08 | 2027-02-07: 50; 2027-02-14: 50; 2027-02-21: 50; 2027-02-28: 50 | x
| ECx Tech-A | TBD | 120 | 200 | 24000 | 2500 | 4 | 10000 | 34000 | 2027-02-07 | 2027-02-27 | 5 | 2027-02-08 | 2027-02-07: 50; 2027-02-14: 50; 2027-02-21: 50; 2027-02-28: 50 | x
| ECx Tech-C | TBD | 120 | 200 | 24000 | 2501 | 4 | 10004 | 34004 | 2027-02-07 | 2027-02-27 | 5 | 2027-02-08 | 2027-02-07: 50; 2027-02-14: 50; 2027-02-21: 50; 2027-02-28: 50 | x
| Lead MCx-A | TBD | 150 | 200 | 30000 | 2500 | 4 | 10000 | 40000 | 2027-02-07 | 2027-02-27 | 5 | 2027-02-08 | 2027-02-07: 50; 2027-02-14: 50; 2027-02-21: 50; 2027-02-28: 50 | x
| MCx Tech-A | TBD | 120 | 200 | 24000 | 2500 | 4 | 10000 | 34000 | 2027-02-07 | 2027-02-27 | 5 | 2027-02-08 | 2027-02-07: 50; 2027-02-14: 50; 2027-02-21: 50; 2027-02-28: 50 | x
| MCx Tech-C | TBD | 120 | 200 | 24000 | 2502 | 4 | 10008 | 34008 | 2027-02-07 | 2027-02-27 | 5 | 2027-02-08 | 2027-02-07: 50; 2027-02-14: 50; 2027-02-21: 50; 2027-02-28: 50 | x
| Phase 6 - L5 IST (2 weeks) | [85 empty] | x
| Lead ECx-A | TBD | 150 | 100 | 15000 | 2500 | 2 | 5000 | 20000 | 2027-03-07 | 2027-03-13 | 3 | 2027-03-08 | 2027-03-07: 50; 2027-03-14: 50 | x
| ECx Tech-A | TBD | 120 | 100 | 12000 | 2500 | 2 | 5000 | 17000 | 2027-03-07 | 2027-03-13 | 3 | 2027-03-08 | 2027-03-07: 50; 2027-03-14: 50 | x
| ECx Tech-C | TBD | 120 | 100 | 12000 | 2501 | 2 | 5002 | 17002 | 2027-03-07 | 2027-03-13 | 3 | 2027-03-08 | 2027-03-07: 50; 2027-03-14: 50 | x
| Lead MCx-A | TBD | 150 | 100 | 15000 | 2500 | 2 | 5000 | 20000 | 2027-03-07 | 2027-03-13 | 3 | 2027-03-08 | 2027-03-07: 50; 2027-03-14: 50 | x
| MCx Tech-A | TBD | 120 | 100 | 12000 | 2500 | 2 | 5000 | 17000 | 2027-03-07 | 2027-03-13 | 3 | 2027-03-08 | 2027-03-07: 50; 2027-03-14: 50 | x
| MCx Tech-C | TBD | 120 | 100 | 12000 | 2502 | 2 | 5004 | 17004 | 2027-03-07 | 2027-03-13 | 3 | 2027-03-08 | 2027-03-07: 50; 2027-03-14: 50 | x
Phase 5 - Data Halls L4-L5 |  |  |  | 1800 | 234000 |  |  | 90018 | 324018
Grand Total |  |  |  | 40910 | 6172900 |  |  | 2030079 | 8202979
6558779
[8 empty] | 216 | 30364.7176 |  |  | Grey Team | Cx Manager | 50 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 30 | 50 | 50 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0
[12 empty] | Grey Team | Cx Scheduler/Coordinator | 50 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 30 | 50 | 50 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0
[5 empty] | 150.8898 |  |  |  | 200.5128 |  |  | Grey Team | Doc Control-A | 50 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 30 | 50 | 50 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0
[12 empty] | Grey Team | Doc Control-B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 9590 | 23.76%
[12 empty] | Blue Team | Lead ECx-A | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 50 | 30 | 50 | 50 | 30 | 30 | 50 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0
[12 empty] | Blue Team | Lead ECx-B | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Blue Team | Lead MCx-A | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 50 | 30 | 50 | 50 | 30 | 30 | 50 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0
[12 empty] | Blue Team | Lead MCx-B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Blue Team | ECx Tech-A | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 50 | 30 | 50 | 50 | 30 | 30 | 50 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0
[12 empty] | Blue Team | ECx Tech-B | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Blue Team | MCx Tech-A | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 50 | 30 | 50 | 50 | 30 | 30 | 50 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0
[12 empty] | Blue Team | MCx Tech-B | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 16390 | 40.6%
[12 empty] | Yellow Team | Lead ECx-C | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Yellow Team | Lead ECx-D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 30 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Yellow Team | Lead MCx-C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 30 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Yellow Team | Lead MCx-D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Yellow Team | ECx Tech-C | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 50 | 30 | 50 | 50 | 30 | 30 | 50 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0
[12 empty] | Yellow Team | ECx Tech-D | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 40 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[12 empty] | Yellow Team | MCx Tech-C | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 30 | 50 | 50 | 30 | 30 | 50 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0
[12 empty] | Yellow Team | MCx Tech-D | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 50 | 50 | 50 | 50 | 50 | 30 | 50 | 50 | 30 | 30 | 50 | 50 | 50 | 50 | 50 | 50 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 14390 | 35.65%
[13 empty] | Total Labor Hours Allocated by Week: | 150 | 90 | 90 | 150 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 600 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 750 | 600 | 750 | 750 | 900 | 800 | 800 | 800 | 800 | 800 | 900 | 600 | 600 | 600 | 600 | 600 | 900 | 600 | 600 | 600 | 600 | 850 | 390 | 600 | 550 | 300 | 300 | 750 | 450 | 450 | 450 | 450 | 750 | 450 | 450 | 450 | 400 | 350 | 100 | 0 | 0 | [5 empty] | 40370 | 100%
[13 empty] | Total Resources Allocated by Week: | 3 | 1.8 | 2.8125 | 4.6875 | 11 | 11 | 11 | 11 | 11 | 11 | 11 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 18 | 16 | 16 | 16 | 16 | 16 | 18 | 12 | 12 | 12 | 12 | 12 | 18 | 12 | 12 | 12 | 12 | 17 | 13 | 12 | 11 | 10 | 10 | 15 | 9 | 9 | 9 | 9 | 15 | 9 | 9 | 9 | 8 | 7 | 2 | 0 | 0

## Tables
Role | Hourly Rate
Cx Manager | 185
Lead MCx-D | 150
Lead MCx-C | 150
Lead MCx-B | 150
Lead MCx-A | 150
Lead ECx-D | 150
Lead ECx-C | 150
Lead ECx-B | 150
Lead ECx-A | 150
Cx Scheduler/Coordinator | 165
MCx Tech-D | 120
MCx Tech-C | 120
MCx Tech-B | 120
MCx Tech-A | 120
ECx Tech-D | 120
ECx Tech-C | 120
ECx Tech-B | 120
ECx Tech-A | 120
Doc Control-B | 110
Doc Control-A | 110
Mech Floater | 125
Elect Floater | 125
D2C Mech Engineering SME | 185
Substation Elecrical Engineering SME | 185

## Equipment_List_Commissioning
Phase 1 | Phase 2 | Phase 3 | Phase 4 | Phase 5 | Phase 6 | Location | Equipment Type | Quantity | Per Phase | OEM | Description | Voltage/Rating | Notes | Commissioning Level | Per Block Quantity | Total Blocks | L2 | L3 | L4 | L5 | L6 | Total Hours | L2 Total Hours | L3 Total Hours | L4 Total Hours | L5 Total Hours | PM & Coordination | Switchyard | Phase 1 Labor Hours | Phase 2 Labor Hours | Phase 3 Labor Hours | Phase 4 Labor Hours | Phase 5 Labor Hours | Phase 6 Labor Hours | Total All Phases
32 | 32 | 32 | 32 | 32 | 32 | Gray Space - Outdoor | Transformer - Data Hall IT | 192 | 32 | TBD | 34.5kV - 480V 2.5MVA |  | All 6 data halls | Level 4 | 32 | 6 | 0.9 | 1.6 | 0.73728 | 0.5 | 0.5 | 4.2373 | 172.8 | 307.2 | 141.5578 | 96 |  |  | 135.593 | 135.593 | 135.593 | 135.593 | 135.593 | 135.593 | 813.5578
12 | 12 | 12 | 12 | 12 | 12 | Gray Space - Outdoor | Transformer - Data Hall Mech | 72 | 12 | TBD | 34.5kV - 480V 5MVA |  | All 6 data halls | Level 4 | 12 | 6 | 0.9 | 1.6 | 0.73728 | 0.5 | 0.5 | 4.2373 | 64.8 | 115.2 | 53.0842 | 36 |  |  | 50.8474 | 50.8474 | 50.8474 | 50.8474 | 50.8474 | 50.8474 | 305.0842
8 | 8 | 8 | 8 | 8 | 8 | Gray Space - Outdoor | Transformer - Network IT | 8 | 8 | TBD | 34.5kV - 480V 2MVA |  | Network Room | Level 4 | 8 | 1 | 0.9 | 1.6 | 0.73728 | 0.5 | 0.5 | 4.2373 | 7.2 | 12.8 | 5.8982 | 4 |  |  | 33.8982 | 33.8982 | 33.8982 | 33.8982 | 33.8982 | 33.8982 | 203.3894
4 | 4 | 4 | 4 | 4 | 4 | Gray Space - Outdoor | Transformer - Network Mech | 4 | 4 | TBD | 34.5kV - 480V 3MVA |  | Network Room | Level 4 | 4 | 1 | 0.9 | 1.6 | 0.73728 | 0.5 | 0.5 | 4.2373 | 3.6 | 6.4 | 2.9491 | 2 |  |  | 16.9491 | 16.9491 | 16.9491 | 16.9491 | 16.9491 | 16.9491 | 101.6947
23 | 23 | 23 | 23 | 23 | 23 | Gray Space - Outdoor | Ring Main Unit | 138 | 23 | TBD | 34.5kV |  | Per switchyard/distribution | Level 4 | 23 | 6 | 0.9 | 1.6 | 0.73728 | 0.5 | 0.5 | 4.2373 | 124.2 | 220.8 | 101.7446 | 69 |  |  | 97.4574 | 97.4574 | 97.4574 | 97.4574 | 97.4574 | 97.4574 | 584.7446
2 | 2 | 2 | 2 | 2 | 2 | Gray Space - Outdoor | MV Switchboard | 12 | 2 | TBD | 34.5kV |  | Switchyard | Level 4 | 2 | 6 | 2.7 | 4.8 | 2.2118 | 0.5 | 0.5 | 10.7118 | 32.4 | 57.6 | 26.5421 | 6 |  |  | 21.4237 | 21.4237 | 21.4237 | 21.4237 | 21.4237 | 21.4237 | 128.5421
27 | 27 | 27 | 27 | 27 | 27 | Gray Space - Outdoor | Chiller | 162 | 27 | Vertiv | Vertiv OFC |  | All 6 data halls | Level 4 | 27 | 6 | 1.35 | 1.6 | 1.4746 | 0.5 | 0.5 | 5.4246 | 218.7 | 259.2 | 238.8787 | 81 |  |  | 146.4631 | 146.4631 | 146.4631 | 146.4631 | 146.4631 | 146.4631 | 878.7787
27 | 27 | 27 | 27 | 27 | 27 | Gray Space - Outdoor | Buffer Tank | 162 | 27 | TBD |  |  | All 6 data halls | Level 4 | 27 | 6 | 0.45 | 0.8 | 0.73728 | 0.5 | 0.5 | 2.9873 | 72.9 | 129.6 | 119.4394 | 81 |  |  | 80.6566 | 80.6566 | 80.6566 | 80.6566 | 80.6566 | 80.6566 | 483.9394
32 | 32 | 32 | 32 | 32 | 32 | Gray Space - Indoor | LV Switchboard - Data Hall Elec | 192 | 32 | Vertiv | 4000A | 480V | All 6 data halls | Level 4 | 32 | 6 | 2.7 | 3.2 | 1.4746 | 0.5 | 0.5 | 8.3746 | 518.4 | 614.4 | 283.1155 | 96 |  |  | 267.9859 | 267.9859 | 267.9859 | 267.9859 | 267.9859 | 267.9859 | 1607.9155
12 | 12 | 12 | 12 | 12 | 12 | Gray Space - Indoor | LV Switchboard - Data Hall Mech | 72 | 12 | Vertiv | 5000A | 480V | All 6 data halls | Level 4 | 12 | 6 | 1.8 | 3.2 | 1.4746 | 0.5 | 0.5 | 7.4746 | 129.6 | 230.4 | 106.1683 | 36 |  |  | 89.6947 | 89.6947 | 89.6947 | 89.6947 | 89.6947 | 89.6947 | 538.1683
8 | 0 | 0 | 0 | 0 | 0 | Gray Space - Indoor | LV Switchboard - Network Elec | 8 | 8 | Vertiv | 4000A | 480V | Network Room | Level 4 | 8 | 1 | 2.7 | 3.2 | 1.4746 | 0.5 | 0.5 | 8.3746 | 21.6 | 25.6 | 11.7965 | 4 |  |  | 66.9965 | 0 | 0 | 0 | 0 | 0 | 66.9965
4 | 0 | 0 | 0 | 0 | 0 | Gray Space - Indoor | LV Switchboard - Network Mech | 4 | 4 | Vertiv | 4000A | 480V | Network Room | Level 4 | 4 | 1 | 2.7 | 3.2 | 1.4746 | 0.5 | 0.5 | 8.3746 | 10.8 | 12.8 | 5.8982 | 2 |  |  | 33.4982 | 0 | 0 | 0 | 0 | 0 | 33.4982
113 | 113 | 113 | 113 | 113 | 113 | Gray Space - Indoor | UPS | 676 | 112 | Vertiv | 480V APM2 600kVA |  | All 6 data halls + Network | Level 4 | 113 | 6 | 0.9 | 2.4 | 1.8432 | 0.5 | 0.5 | 6.1432 | 608.4 | 1622.4 | 1246.0032 | 338 |  |  | 694.1816 | 694.1816 | 694.1816 | 694.1816 | 694.1816 | 694.1816 | 4165.0896
11 | 11 | 11 | 11 | 11 | 11 | Gray Space - Indoor | CRAH Fan Wall - Electrical Room | 64 | 10 | Vertiv | CA606 |  | Electrical rooms | Level 4 | 11 | 6 | 1.35 | 2.4 | 0.73728 | 0.5 | 0.5 | 5.4873 | 86.4 | 153.6 | 47.1859 | 32 |  |  | 60.3601 | 60.3601 | 60.3601 | 60.3601 | 60.3601 | 60.3601 | 362.1605
351 | 351 | 351 | 351 | 351 | 351 | Gray Space - Indoor | Battery Cabinets | 2104 | 350 | Vertiv | LI5 - LI7 |  | All 6 data halls + Network | Level 4 | 351 | 6 | 1.35 | 0.8 | 0.36864 | 0.5 | 0.5 | 3.5186 | 2840.4 | 1683.2 | 775.6186 | 1052 |  |  | 1235.0426 | 1235.0426 | 1235.0426 | 1235.0426 | 1235.0426 | 1235.0426 | 7410.2558
[6 empty] | White Space - Option 1 | HAC - SmartRun | 41 | 6 | Vertiv | Hot Aisle Containment |  | Option 1 (not base) | Level 4 | 7 | 6 | 1.8 | 1.6 | 0.73728 | 0.5 | 0.5 | 5.1373 | 73.8 | 65.6 | 30.2285 | 20.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | White Space - Option 1 | Rack Power Panel | 576 | 96 | Vertiv | 1000/1200A | 480V | Option 1 (not base) | Level 4 | 96 | 6 | 0.9 | 1.6 | 1.1059 | 0.5 | 0.5 | 4.6059 | 518.4 | 921.6 | 637.0099 | 288 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | White Space - Option 1 | Remote Distribution Panel | 328 | 54 | Vertiv | 400A RXV Panels | 480V | Option 1 (not base) | Level 4 | 55 | 6 | 1.35 | 1.6 | 1.1059 | 0.5 | 0.5 | 5.0559 | 442.8 | 524.8 | 362.7418 | 164 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | White Space - Option 1 | CDU | 190 | 31 | Vertiv | XDU 2300 |  | Option 1 (not base) | Level 4 | 32 | 6 | 0.9 | 2.4 | 1.4746 | 0.5 | 0.5 | 5.7746 | 171 | 456 | 280.1664 | 95 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | White Space - Option 1 | CRAH Fan Wall - Data Hall | 214 | 35 | Vertiv | CA606 |  | Option 1 (not base) | Level 4 | 36 | 6 | 1.35 | 2.4 | 1.1059 | 0.5 | 0.5 | 5.8559 | 288.9 | 513.6 | 236.6669 | 107 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
10 | 10 | 10 | 10 | 10 | 10 | White Space - Option 2 | HAC - SmartRun | 65 | 10 | Vertiv | Hot Aisle Containment |  | Option 2 (BASE) | Level 4 | 11 | 6 | 1.8 | 3.2 | 0.73728 | 0.5 | 0.5 | 6.7373 | 117 | 208 | 47.9232 | 32.5 |  |  | 67.3728 | 67.3728 | 67.3728 | 67.3728 | 67.3728 | 67.3728 | 404.2368
160 | 160 | 160 | 160 | 160 | 160 | White Space - Option 2 | Rack Power Panel | 960 | 160 | Vertiv | 1000/1200A | 480V | Option 2 (BASE) | Level 4 | 160 | 6 | 0.9 | 1.6 | 1.1059 | 0.5 | 0.5 | 4.6059 | 864 | 1536 | 1061.6832 | 480 |  |  | 736.9472 | 736.9472 | 736.9472 | 736.9472 | 736.9472 | 736.9472 | 4421.6832
7 | 7 | 7 | 7 | 7 | 7 | White Space - Option 2 | Remote Distribution Panel | 40 | 6 | Vertiv | 400A RXV Panels | 480V | Option 2 (BASE) | Level 4 | 7 | 6 | 1.35 | 1.6 | 1.1059 | 0.5 | 0.5 | 5.0559 | 54 | 64 | 44.2368 | 20 |  |  | 35.3914 | 35.3914 | 35.3914 | 35.3914 | 35.3914 | 35.3914 | 212.3486
32 | 32 | 32 | 32 | 32 | 32 | White Space - Option 2 | CDU | 190 | 31 | Vertiv | XDU 2300 |  | Option 2 (BASE) | Level 4 | 32 | 6 | 0.9 | 2.4 | 1.4746 | 0.5 | 0.5 | 5.7746 | 171 | 456 | 280.1664 | 95 |  |  | 184.7859 | 184.7859 | 184.7859 | 184.7859 | 184.7859 | 184.7859 | 1108.7155
36 | 36 | 36 | 36 | 36 | 36 | White Space - Option 2 | CRAH Fan Wall - Data Hall | 214 | 35 | Vertiv | CA606 |  | Option 2 (BASE) | Level 4 | 36 | 6 | 1.35 | 2.4 | 1.1059 | 0.5 | 0.5 | 5.8559 | 288.9 | 513.6 | 236.6669 | 107 |  |  | 210.8131 | 210.8131 | 210.8131 | 210.8131 | 210.8131 | 210.8131 | 1264.8787
[6 empty] | White Space - Option 3 | HAC - SmartRun | 41 | 6 | Vertiv | Hot Aisle Containment |  | Option 3 (not base) | Level 4 | 7 | 6 | 1.8 | 3.2 | 0.73728 | 0.5 | 0.5 | 6.7373 | 73.8 | 131.2 | 30.2285 | 20.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | White Space - Option 3 | Rack Power Panel | 576 | 96 | Vertiv | 1000/1200A | 480V | Option 3 (not base) | Level 4 | 96 | 6 | 0.9 | 1.6 | 1.1059 | 0.5 | 0.5 | 4.6059 | 518.4 | 921.6 | 637.0099 | 288 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | White Space - Option 3 | Remote Distribution Panel | 40 | 6 | Vertiv | 400A RXV Panels | 480V | Option 3 (not base) | Level 4 | 7 | 6 | 1.35 | 1.6 | 1.1059 | 0.5 | 0.5 | 5.0559 | 54 | 64 | 44.2368 | 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | White Space - Option 3 | CDU | 190 | 31 | Vertiv | XDU 2300 |  | Option 3 (not base) | Level 4 | 32 | 6 | 0.9 | 2.4 | 1.4746 | 0.5 | 0.5 | 5.7746 | 171 | 456 | 280.1664 | 95 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | White Space - Option 3 | CRAH Fan Wall - Data Hall | 214 | 35 | Vertiv | CA606 |  | Option 3 (not base) | Level 4 | 36 | 6 | 1.35 | 2.4 | 1.1059 | 0.5 | 0.5 | 5.8559 | 288.9 | 513.6 | 236.6669 | 107 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | PM & Coordination | [22 empty] | 1718.7376 | 1678.2525 | 1678.2525 | 1678.2525 | 1678.2525 | 1678.2525
[17 empty] | 0.81 | [11 empty] | 4266.3586 | 4165.8639 | 4165.8639 | 4165.8639 | 4165.8639 | 4165.8639 | 25095.6782
[17 empty] | 0.81 |  |  |  |  | Total Hours | 9008.1 | 12796.8 | 7611.6787 | 3874.5 | 10110 | 5670 | 5985.0962 | 5844.1164 | 5844.1164 | 5844.1164 | 5844.1164 | 5844.1164 | 40875.6782
0.81
[17 empty] | 0.81 |  |  |  |  | Total Hours/Phase | 1501.35 | 2132.8 | 1268.6131 | 645.75
[17 empty] | 0.81 |  |  |  |  | Total Hours/6-Man Team | 250.225 | 355.4667 | 211.4355 | 107.625
[17 empty] | 2.43 |  |  |  |  | Total Days | 25.0225 | 35.5467 | 21.1436 | 10.7625
[17 empty] | 1.215 |  |  |  |  | Total Weeks | 5.0045 | 7.1093 | 4.2287 | 2.1525
0.405
2.43
1.62
2.43
2.43
0.81
1.215
1.215
1.62
0.81
1.215
0.81
1.215
1.62
0.81
1.215
0.81
1.215
1.62
0.81
1.215
0.81
1.215
0
0.648