## OFE_Equipment_By_Building
Building | Assignment | Seller | OEM | Description | Procurement Status | Quantity Required | Quantity Ordered | Net Short Quantity | Extended Amount | Extended Amount Outstanding | Unit Price | Extended
A | DTO-A | CERIO | DELTA | DELTA-1250KVA-UPS | PO Issued | 10 | 10 | 0 | 3529110 | 0 | 352910.96 | 3529109.6
A | DTO-A | CERIO | DELTA | DELTA-250KVA-UPS | PO Issued | 9 | 9 | 0 | 1071091 | 0 | 119010.13 | 1071091.17
A | DTO-A | CERIO | DELTA | DELTA-400A-BUSWAY | PO Issued | 16 | 16 | 0 | 1225604 | 0 | 76600.24 | 1225603.84
A | DTO-A | CERIO | DELTA | DELTA-600A-BUSWAY | PO Issued | 44 | 44 | 0 | 3370411 | 0 | 76600.24 | 3370410.56
A | DTO-A | CERIO | DELTA | DELTA-63A-PIU | PO Issued | 44 | 44 | 0 | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | #VALUE!
A | DTO-A | JCI | JCI | JCI-72K-FAN WALL | PO Issued | 17 | 17 | 0 | 1934783 | 0 | 113810.76 | 1934782.92
A | DTO-A | JCL ENERGY | JCL ENERGY | JCL ENERGY-2550KVA 13.2KV KNAN-TRANSFORMER | PO Issued | 5 | 5 | 0 | 547475 | 0 | 109495 | 547475
A | DTO-A | JCL ENERGY | JCL ENERGY | JCL ENERGY-2550KVA 13.2KV KNAF-TRANSFORMER | PO Issued | 3 | 3 | 0 | 337785 | 0 | 112595 | 337785
A | DTO-A | MCG | MCFI | MCFI-IT-MODULE | PO Issued | 5 | 5 | 0 | 7033840 | 0 | 1406767.94 | 7033839.7
A | DTO-A | MCG | MCFI | MCFI-MECH-MODULE | PO Issued | 3 | 3 | 0 | 4220304 | 0 | 1406767.94 | 4220303.82
A | DTO-A | SVL | AAON | AAON-RQA-005-DOAS | PO Issued | 2 | 2 | 0 | 133438 | 0 | 66718.75 | 133437.5
A | DTO-A | SVL | CONDAIR | CONDAIR-RS-030-HUMIDIFIER | PO Issued | 3 | 3 | 0 | 34200 | 0 | 11400 | 34200
A | DTO-A | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 2 | 2 | 0 | 145600 | 0 | 72800 | 145600
A | DTO-A | TEXAS AIR SYSTEMS | FISEN | FISEN-YVFA0459-CHILLED WATER PUMP SKID | PO Issued | 9 | 9 | 0 | 724122 | 0 | 80458 | 724122
A | DTO-A | TEXAS AIR SYSTEMS | WENDLAND | WENDLAND-15000 GAL HORIZONTAL-THERMAL STORAGE TANK | PO Issued | 2 | 2 | 0 | 815898 | 0 | 407949 | 815898
A-MMR | DTO-A-MMR | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 4 | 4 | 0 | 291200 | 0 | 72800 | 291200
B | DTO-B | CERIO | DELTA | DELTA-1250KVA-UPS | PO Issued | 42 | 42 | 0 | 14822260 | 0 | 352910.96 | 14822260.32
B | DTO-B | CERIO | DELTA | DELTA-250KVA-UPS | PO Issued | 30 | 30 | 0 | 3570304 | 0 | 119010.13 | 3570303.9
B | DTO-B | HYDRAQUIP | DANFOSS | DANFOSS-2" FD83-COUPLER | PO Issued | 1200 | 1200 | 0 | 631560 | 0 | 526.3 | 631560
B | DTO-B | CERIO | DELTA | DELTA-800A-STS | PO Issued | 72 | 212 | 140 | 6670800 | -12971000 | 92650 | 19641800
B | DTO-B | CERIO | DELTA | DELTA-600A-BUSWAY | PO Issued | 16 | 16 | 0 | 1225604 | 0 | 76600.24 | 1225603.84
B | DTO-B | CERIO | DELTA | DELTA-400A-BUSWAY | PO Issued | 2 | 2 | 0 | 153200 | 0 | 76600.24 | 153200.48
B | DTO-B | CERIO | DELTA | DELTA-800A-BUSWAY | PO Issued | 72 | 72 | 0 | 5515217 | 0 | 76600.24 | 5515217.28
B | DTO-B | CERIO | DELTA | DELTA-63A-PIU | PO Issued | 72 | 72 | 0 | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | #VALUE!
B | DTO-B | CERIO | KOHLER | KOHLER-3MW-GENERATOR | PO Issued | 4 | 4 | 0 | 9800000 | 0 | 2450000 | 9800000
B | DTO-B | EAE | EAE | EAE-4000A-RESERVE BUSDUCT | PO Issued | 1114 | 1114 | 0 | 1038248 | 0 | 932 | 1038248
B | DTO-B | EAE | EAE | EAE-800A-RESERVE BUSDUCT TAP BOX | PO Issued | 72 | 72 | 0 | INCLUDED IN RBUS | INCLUDED IN RBUS | INCLUDED IN RBUS | #VALUE!
B | DTO-B | JCI | JCI | JCI-500T-115-CHILLER | PO Issued | 30 | 30 | 0 | 17500846 | 0 | 583361.53 | 17500845.9
B | DTO-B | JCI | JCI | JCI-72K-FAN WALL | PO Issued | 38 | 38 | 0 | 4324809 | 0 | 113810.76 | 4324808.88
B | DTO-B | JCL ENERGY | JCL ENERGY | JCL ENERGY-2550KVA 34.5KV KNAN-TRANSFORMER | PO Issued | 21 | 21 | 0 | 440880 | 0 | 20994.28 | 440879.88
B | DTO-B | JCL ENERGY | JCL ENERGY | JCL ENERGY-2550KVA 34.5KV KNAF-TRANSFORMER | PO Issued | 10 | 10 | 0 | 209943 | 0 | 20994.28 | 209942.8
B | DTO-B | MCG | MCFI | MCFI-MECH-MODULE | PO Issued | 10 | 10 | 0 | 14067679 | 0 | 1406767.94 | 14067679.4
B | DTO-B | MCG | MCFI | MCFI-IT-MODULE | PO Issued | 21 | 21 | 0 | 29542127 | 0 | 1406767.94 | 29542126.74
B | DTO-B | SVL | AAON | AAON-RQA-011-DOAS | PO Issued | 2 | 2 | 0 | 133438 | 0 | 66718.75 | 133437.5
B | DTO-B | SVL | CONDAIR | CONDAIR-RS-030-HUMIDIFIER | PO Issued | 4 | 4 | 0 | 38843 | 0 | 9710.71 | 38842.84
B | DTO-B | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 2 | 2 | 0 | 145600 | 0 | 72800 | 145600
B | DTO-B | TEXAS AIR SYSTEMS | FISEN | FISEN-YVFA0459-CHILLED WATER PUMP SKID | PO Issued | 30 | 30 | 0 | 2413740 | 0 | 80458 | 2413740
B | DTO-B | TEXAS AIR SYSTEMS | WENDLAND | WENDLAND-30000 GAL VERTICAL-THERMAL STORAGE TANK | PO Issued | 4 | 4 | 0 | 1631796 | 0 | 407949 | 1631796
B-MMR | DTO-B-MMR | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 4 | 4 | 0 | 291200 | 0 | 72800 | 291200
C | DTO-C | CERIO | DELTA | DELTA-800A-STS | PO Issued | 72 | 72 | 0 | 6670800 | 0 | 92650 | 6670800
C | DTO-C | CERIO | DELTA | DELTA-1250KVA-UPS | PO Issued | 42 | 42 | 0 | 14822260 | 0 | 352910.96 | 14822260.32
C | DTO-C | CERIO | DELTA | DELTA-250KVA-UPS | PO Issued | 30 | 30 | 0 | 3570304 | 0 | 119010.13 | 3570303.9
C | DTO-C | CERIO | DELTA | DELTA-400A-BUSWAY | PO Issued | 2 | 2 | 0 | 153200 | 0 | 76600.24 | 153200.48
C | DTO-C | CERIO | DELTA | DELTA-600A-BUSWAY | PO Issued | 16 | 16 | 0 | 1225604 | 0 | 76600.24 | 1225603.84
C | DTO-C | CERIO | DELTA | DELTA-800A-BUSWAY | PO Issued | 72 | 72 | 0 | 5515217 | 0 | 76600.24 | 5515217.28
C | DTO-C | CERIO | DELTA | DELTA-63A-PIU | PO Issued | 72 | 72 | 0 | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | #VALUE!
C | DTO-C | HYDRAQUIP | DANFOSS | DANFOSS-2" FD83-COUPLER | PO Issued | 1200 | 1200 | 0 | 631560 | 0 | 526.3 | 631560
C | DTO-C | CERIO | KOHLER | KOHLER-3MW-GENERATOR | PO Issued | 4 | 4 | 0 | 9800000 | 0 | 2450000 | 9800000
C | DTO-C | EAE | EAE | EAE-4000A-RESERVE BUSDUCT | PO Issued | 1108 | 1108 | 0 | 1032656 | 0 | 932 | 1032656
C | DTO-C | EAE | EAE | EAE-800A-RESERVE BUSDUCT TAP BOX | PO Issued | 72 | 72 | 0 | INCLUDED IN RBUS | INCLUDED IN RBUS | INCLUDED IN RBUS | #VALUE!
C | DTO-C | JCI | JCI | JCI-500T-115-CHILLER | PO Issued | 30 | 30 | 0 | 17500846 | 0 | 583361.53 | 17500845.9
C | DTO-C | JCI | JCI | JCI-72K-FAN WALL | PO Issued | 38 | 38 | 0 | 4324809 | 0 | 113810.76 | 4324808.88
C | DTO-C | JCL ENERGY | JCL ENERGY | JCL ENERGY-2550KVA 34.5KV KNAN-TRANSFORMER | PO Issued | 21 | 21 | 0 | 440880 | 0 | 20994.28 | 440879.88
C | DTO-C | JCL ENERGY | JCL ENERGY | JCL ENERGY-2550KVA 34.5KV KNAF-TRANSFORMER | PO Issued | 10 | 10 | 0 | 209943 | 0 | 20994.28 | 209942.8
C | DTO-C | MCG | MCFI | MCFI-IT-MODULE | PO Issued | 21 | 21 | 0 | 29542127 | 0 | 1406767.94 | 29542126.74
C | DTO-C | MCG | MCFI | MCFI-MECH-MODULE | PO Issued | 10 | 10 | 0 | 14067679 | 0 | 1406767.94 | 14067679.4
C | DTO-C | SVL | AAON | AAON-RQA-011-DOAS | PO Issued | 2 | 2 | 0 | 133438 | 0 | 66718.75 | 133437.5
C | DTO-C | SVL | CONDAIR | CONDAIR-RS-030-HUMIDIFIER | PO Issued | 4 | 4 | 0 | 38843 | 0 | 9710.71 | 38842.84
C | DTO-C | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 2 | 2 | 0 | 145600 | 0 | 72800 | 145600
C | DTO-C | TEXAS AIR SYSTEMS | FISEN | FISEN-YVFA0459-CHILLED WATER PUMP SKID | PO Issued | 30 | 30 | 0 | 2413740 | 0 | 80458 | 2413740
C | DTO-C | TEXAS AIR SYSTEMS | WENDLAND | WENDLAND-30000 GAL VERTICAL-THERMAL STORAGE TANK | PO Issued | 4 | 4 | 0 | 1631796 | 0 | 407949 | 1631796
C-MMR | DTO-C-MMR | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 4 | 4 | 0 | 291200 | 0 | 72800 | 291200
D | DTO-D | CERIO | DELTA | DELTA-1250KVA-UPS | PO Issued | 42 | 42 | 0 | 14822260 | 0 | 352910.96 | 14822260.32
D | DTO-D | CERIO | DELTA | DELTA-250KVA-UPS | PO Issued | 30 | 30 | 0 | 3570304 | 0 | 119010.13 | 3570303.9
D | DTO-D | CERIO | DELTA | DELTA-800A-STS | PO Issued | 72 | 72 | 0 | 6670800 | 0 | 92650 | 6670800
D | DTO-D | CERIO | DELTA | DELTA-400A-BUSWAY | PO Issued | 2 | 2 | 0 | 153200 | 0 | 76600.24 | 153200.48
D | DTO-D | CERIO | DELTA | DELTA-600A-BUSWAY | PO Issued | 16 | 16 | 0 | 1225604 | 0 | 76600.24 | 1225603.84
D | DTO-D | CERIO | DELTA | DELTA-800A-BUSWAY | PO Issued | 72 | 72 | 0 | 5515217 | 0 | 76600.24 | 5515217.28
D | DTO-D | CERIO | DELTA | DELTA-63A-PIU | PO Issued | 72 | 72 | 0 | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | #VALUE!
D | DTO-D | CERIO | KOHLER | KOHLER-3MW-GENERATOR | PO Issued | 4 | 4 | 0 | 9800000 | 0 | 2450000 | 9800000
D | DTO-D | EAE | EAE | EAE-4000A-RESERVE BUSDUCT | PO Issued | 1108 | 1108 | 0 | 1032656 | 0 | 932 | 1032656
D | DTO-D | EAE | EAE | EAE-800A-RESERVE BUSDUCT TAP BOX | PO Issued | 72 | 72 | 0 | INCLUDED IN RBUS | INCLUDED IN RBUS | INCLUDED IN RBUS | #VALUE!
D | DTO-D | JCI | JCI | JCI-500T-115-CHILLER | PO Issued | 30 | 30 | 0 | 17500846 | 0 | 583361.53 | 17500845.9
D | DTO-D | JCI | JCI | JCI-72K-FAN WALL | PO Issued | 38 | 38 | 0 | 4324809 | 0 | 113810.76 | 4324808.88
D | DTO-D | JCL ENERGY | VTC | VTC-2550KVA 34.5KV KNAN-TRANSFORMER | PO Issued | 21 | 21 | 0 | 440880 | 0 | 20994.28 | 440879.88
D | DTO-D | JCL ENERGY | VTC | VTC-2550KVA 34.5KV KNAF-TRANSFORMER | PO Issued | 10 | 10 | 0 | 209943 | 0 | 20994.28 | 209942.8
D | DTO-D | MCG | MCFI | MCFI-IT-MODULE | PO Issued | 21 | 21 | 0 | 29542127 | 0 | 1406767.94 | 29542126.74
D | DTO-D | MCG | MCFI | MCFI-MECH-MODULE | PO Issued | 10 | 10 | 0 | 14067679 | 0 | 1406767.94 | 14067679.4
D | DTO-D | SVL | AAON | AAON-RQA-011-DOAS | PO Issued | 2 | 2 | 0 | 133438 | 0 | 66718.75 | 133437.5
D | DTO-D | HYDRAQUIP | DANFOSS | DANFOSS-2" FD83-COUPLER | PO Issued | 1200 | 1200 | 0 | 631560 | 0 | 526.3 | 631560
D | DTO-D | SVL | CONDAIR | CONDAIR-RS-030-HUMIDIFIER | PO Issued | 4 | 4 | 0 | 38843 | 0 | 9710.71 | 38842.84
D | DTO-D | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 2 | 2 | 0 | 145600 | 0 | 72800 | 145600
D | DTO-D | TEXAS AIR SYSTEMS | FISEN | FISEN-YVFA0459-CHILLED WATER PUMP SKID | PO Issued | 30 | 30 | 0 | 2413740 | 0 | 80458 | 2413740
D | DTO-D | TEXAS AIR SYSTEMS | WENDLAND | WENDLAND-30000 GAL HORIZONTAL-THERMAL STORAGE TANK | PO Issued | 4 | 4 | 0 | 1631796 | 0 | 407949 | 1631796
D | DTO-D | MCG | ABB | ABB-38KV 330-MV SWG | PO Issued | 6 | 6 | 0 | 1100000 | 0 | 183333.33 | 1099999.98
D | DTO-D | MCG | ABB | ABB-38KV 210-MV SWG | PO Issued | 6 | 6 | 0 | 1100000 | 0 | 183333.33 | 1099999.98
D-MMR | DTO-D-MMR | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 4 | 4 | 0 | 291200 | 0 | 72800 | 291200
E | DTO-E | CERIO | DELTA | DELTA-1250KVA-UPS | PO Issued | 10 | 10 | 0 | 3529110 | 0 | 352910.96 | 3529109.6
E | DTO-E | CERIO | DELTA | DELTA-250KVA-UPS | PO Issued | 9 | 9 | 0 | 1071091 | 0 | 119010.13 | 1071091.17
E | DTO-E | CERIO | DELTA | DELTA-400A-BUSWAY | PO Issued | 16 | 16 | 0 | 1225604 | 0 | 76600.24 | 1225603.84
E | DTO-E | CERIO | DELTA | DELTA-600A-BUSWAY | PO Issued | 44 | 44 | 0 | 3370411 | 0 | 76600.24 | 3370410.56
E | DTO-E | CERIO | DELTA | DELTA-63A-PIU | PO Issued | 88 | 88 | 0 | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | #VALUE!
E | DTO-E | GIGA ENERGY | GIGA ENERGY | GIGA ENERGY-2550KVA 18KV KNAN-TRANSFORMER | PO Issued | 5 | 5 | 0 | 391585 | 0 | 78317 | 391585
E | DTO-E | GIGA ENERGY | GIGA ENERGY | GIGA ENERGY-2550KVA 18KV KNAF-TRANSFORMER | PO Issued | 3 | 3 | 0 | 281943 | 0 | 93981 | 281943
E | DTO-E | JCI | JCI | JCI-500T-115-CHILLER | PO Issued | 9 | 9 | 0 | 5250254 | 0 | 583361.53 | 5250253.77
E | DTO-E | JCI | JCI | JCI-72K-FAN WALL | PO Issued | 17 | 17 | 0 | 1934783 | 0 | 113810.76 | 1934782.92
E | DTO-E | SVL | SVL | SVL-IST CX SUPPORT-CAMPUS | PO Issued | 1 | 1 | 0 | 186300 | 0 | 186300 | 186300
E | DTO-E | TEXAS AIR SYSTEMS | TEXAS AIR SYSTEMS | TAS-IST CX SUPPORT-CAMPUS | PO Issued | 1 | 1 | 0 | 419530 | 0 | 419530 | 419530
E | DTO-E | MCG | KOHLER | KOHLER-2.8MW-GENERATOR | PO Issued | 4 | 4 | 0 | 5880000 | 0 | 1470000 | 5880000
E | DTO-E | JCI | JCI | JCI-HAIL LOUVERS-CHILLER | PO Pending Approval | 189 | 0 | -189 | 1663200 | 1663200 | 8800 | 0
E | DTO-E | JCI | JCI | JCI-FAN WALL FILTER RACK G1-REPAIR | PO Pending Approval | 1 | 0 | -1 | 16875 | 16875 | 16875 | 0
E | DTO-E | JCI | JCI | JCI-FAN WALL FILTER RACK G2-REPAIR | PO Pending Approval | 1 | 0 | -1 | 17815 | 17815 | 17815 | 0
E | DTO-E | JCI | JCI | JCI-FAN WALL IST CX-OVERTIME | PO Pending Approval | 1 | 0 | -1 | 35630 | 35630 | 35630 | 0
E | DTO-E | STARLINE | STARLINE | STARLINE-L2 CX-BUSWAY | PO Issued | 1 | 1 | 0 | 12050 | 0 | 12050 | 12050
E | DTO-E | MCG | MCFI | MCFI-IT-MODULE | PO Issued | 5 | 5 | 0 | 7033840 | 0 | 1406767.94 | 7033839.7
E | DTO-E | MCG | MCFI | MCFI-MECH-MODULE | PO Issued | 3 | 3 | 0 | 4220304 | 0 | 1406767.94 | 4220303.82
E | DTO-E | MCG | MCFI | KOHLER-3.5MW-GENERATOR | PO Issued | 2 | 2 | 0 | 4921000 | 0 | 2460500 | 4921000
E | DTO-E | MCG | POINT EIGHT POWER | PEP-1.25MW CAT-SWITCHBOARD | PO Issued | 2 | 2 | 0 | 731900 | 0 | 365949.82 | 731899.64
E | DTO-E | SVL | AAON | AAON-RQA-005-DOAS | PO Issued | 2 | 2 | 0 | 133438 | 0 | 66718.75 | 133437.5
E | DTO-E | SVL | CONDAIR | CONDAIR-RS-030-HUMIDIFIER | PO Issued | 3 | 3 | 0 | 34200 | 0 | 11400 | 34200
E | DTO-E | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 2 | 2 | 0 | 145600 | 0 | 72800 | 145600
E | DTO-E | MCG | CUMMINS | CUMMINS-70A-ATS | PO Issued | 8 | 8 | 0 | 94811 | 0 | 11851.38 | 94811.04
E | DTO-E | T5 | CAT | CAT-1.25MW-GENERATOR | PO Issued | 4 | 4 | 0 | 3310730 | 0 | 827682.44 | 3310729.76
E | DTO-E | TEXAS AIR SYSTEMS | FISEN | FISEN-YVFA0459-CHILLED WATER PUMP SKID | PO Issued | 9 | 9 | 0 | 724122 | 0 | 80458 | 724122
E | DTO-E | TEXAS AIR SYSTEMS | WENDLAND | WENDLAND-15000 GAL HORIZONTAL-THERMAL STORAGE TANK | PO Issued | 2 | 2 | 0 | 815898 | 0 | 407949 | 815898
E-MMR | DTO-E-MMR | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 4 | 4 | 0 | 291200 | 0 | 72800 | 291200
F | DTO-F | CERIO | DELTA | DELTA-1250KVA-UPS | PO Issued | 42 | 42 | 0 | 14822260 | 0 | 352910.96 | 14822260.32
F | DTO-F | CERIO | DELTA | DELTA-250KVA-UPS | PO Issued | 30 | 30 | 0 | 3570304 | 0 | 119010.13 | 3570303.9
F | DTO-F | CERIO | DELTA | DELTA-400A-BUSWAY | PO Issued | 2 | 2 | 0 | 153200 | 0 | 76600.24 | 153200.48
F | DTO-F | CERIO | DELTA | DELTA-600A-BUSWAY | PO Issued | 16 | 16 | 0 | 1225604 | 0 | 76600.24 | 1225603.84
F | DTO-F | CERIO | DELTA | DELTA-800A-BUSWAY | PO Issued | 72 | 72 | 0 | 5515217 | 0 | 76600.24 | 5515217.28
F | DTO-F | EAE | EAE | EAE-4000A-RESERVE BUSDUCT | PO Issued | 1095 | 1095 | 0 | 1020540 | 0 | 932 | 1020540
F | DTO-F | EAE | EAE | EAE-800A-RESERVE BUSDUCT TAP BOX | PO Issued | 72 | 72 | 0 | INCLUDED IN RBUS | INCLUDED IN RBUS | INCLUDED IN RBUS | #VALUE!
F | DTO-F | GIGA ENERGY | GIGA ENERGY | GIGA ENERGY-2550KVA 18KV KNAN-TRANSFORMER | PO Issued | 21 | 21 | 0 | 1644657 | 0 | 78317 | 1644657
F | DTO-F | GIGA ENERGY | GIGA ENERGY | GIGA ENERGY-2550KVA 18KV KNAF-TRANSFORMER | PO Issued | 10 | 10 | 0 | 939810 | 0 | 93981 | 939810
F | DTO-F | JCI | JCI | JCI-500T-115-CHILLER | PO Issued | 30 | 30 | 0 | 17500846 | 0 | 583361.53 | 17500845.9
F | DTO-F | JCI | JCI | JCI-72K-FAN WALL | PO Issued | 38 | 38 | 0 | 4324809 | 0 | 113810.76 | 4324808.88
F | DTO-F | HYDRAQUIP | DANFOSS | DANFOSS-2" FD83-COUPLER | PO Issued | 1200 | 1200 | 0 | 631560 | 0 | 526.3 | 631560
F | DTO-F | MCG | MCFI | MCFI-IT-MODULE | PO Issued | 21 | 21 | 0 | 29542127 | 0 | 1406767.94 | 29542126.74
F | DTO-F | MCG | MCFI | MCFI-MECH-MODULE | PO Issued | 10 | 10 | 0 | 14067679 | 0 | 1406767.94 | 14067679.4
F | DTO-F | MCG | POINT EIGHT POWER | PEP-1.25MW CAT-SWITCHBOARD | PO Issued | 4 | 4 | 0 | 1463799 | 0 | 365949.82 | 1463799.28
F | DTO-F | SVL | AAON | AAON-RQA-011-DOAS | PO Issued | 2 | 2 | 0 | 133438 | 0 | 66718.75 | 133437.5
F | DTO-F | SVL | CONDAIR | CONDAIR-RS-030-HUMIDIFIER | PO Issued | 8 | 8 | 0 | 77686 | 0 | 9710.71 | 77685.68
F | DTO-F | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 2 | 2 | 0 | 145600 | 0 | 72800 | 145600
F | DTO-F | T5 | CAT | CAT-1.25MW-GENERATOR | PO Issued | 8 | 8 | 0 | 6621459 | 0 | 827682.44 | 6621459.52
F | DTO-F | TEXAS AIR SYSTEMS | FISEN | FISEN-YVFA0459-CHILLED WATER PUMP SKID | PO Issued | 30 | 30 | 0 | 2413740 | 0 | 80458 | 2413740
F | DTO-F | TEXAS AIR SYSTEMS | WENDLAND | WENDLAND-30000 GAL VERTICAL-THERMAL STORAGE TANK | PO Issued | 4 | 4 | 0 | 1631796 | 0 | 407949 | 1631796
F | DTO-F | CERIO | DELTA | DELTA-800A-STS | PO Issued | 72 | 72 | 0 | 6670800 | 0 | 92650 | 6670800
F | DTO-F | CERIO | DELTA | DELTA-63A-PIU | PO Issued | 72 | 72 | 0 | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | #VALUE!
F-MMR | DTO-F-MMR | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 4 | 4 | 0 | 291200 | 0 | 72800 | 291200
G | DTO-G | CERIO | DELTA | DELTA-1250KVA-UPS | PO Issued | 42 | 42 | 0 | 14822260 | 0 | 352910.96 | 14822260.32
G | DTO-G | CERIO | DELTA | DELTA-250KVA-UPS | PO Issued | 30 | 30 | 0 | 3570304 | 0 | 119010.13 | 3570303.9
G | DTO-G | CERIO | DELTA | DELTA-400A-BUSWAY | PO Issued | 2 | 2 | 0 | 153200 | 0 | 76600.24 | 153200.48
G | DTO-G | CERIO | DELTA | DELTA-600A-BUSWAY | PO Issued | 16 | 16 | 0 | 1225604 | 0 | 76600.24 | 1225603.84
G | DTO-G | CERIO | DELTA | DELTA-800A-BUSWAY | PO Issued | 32 | 32 | 0 | 2451208 | 0 | 76600.24 | 2451207.68
G | DTO-G | CERIO | DELTA | DELTA-63A-PIU | PO Issued | 72 | 72 | 0 | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | #VALUE!
G | DTO-G | CERIO | KOHLER | KOHLER-3MW-GENERATOR | PO Issued | 2 | 2 | 0 | 1125346 | 0 | 562672.88 | 1125345.76
G | DTO-G | EAE | EAE | EAE-4000A-RESERVE BUSDUCT | PO Issued | 1095 | 1095 | 0 | 1020540 | 0 | 932 | 1020540
G | DTO-G | EAE | EAE | EAE-800A-RESERVE BUSDUCT TAP BOX | PO Issued | 72 | 72 | 0 | INCLUDED IN RBUS | INCLUDED IN RBUS | INCLUDED IN RBUS | #VALUE!
G | DTO-G | GIGA ENERGY | GIGA ENERGY | GIGA ENERGY-2550KVA 18KV KNAN-TRANSFORMER | PO Issued | 21 | 21 | 0 | 1644657 | 0 | 78317 | 1644657
G | DTO-G | GIGA ENERGY | GIGA ENERGY | GIGA ENERGY-2550KVA 18KV KNAF-TRANSFORMER | PO Issued | 10 | 10 | 0 | 939810 | 0 | 93981 | 939810
G | DTO-G | JCI | JCI | JCI-500T-115-CHILLER | PO Issued | 30 | 30 | 0 | 17500846 | 0 | 583361.53 | 17500845.9
G | DTO-G | JCI | JCI | JCI-72K-FAN WALL | PO Issued | 38 | 38 | 0 | 4324809 | 0 | 113810.76 | 4324808.88
G | DTO-G | MCG | KOHLER | KOHLER-2.8MW-GENERATOR | PO Issued | 1 | 1 | 0 | 1470000 | 0 | 1470000 | 1470000
G | DTO-G | MCG | MCFI | MCFI-IT-MODULE | PO Issued | 21 | 21 | 0 | 29542127 | 0 | 1406767.94 | 29542126.74
G | DTO-G | MCG | MCFI | MCFI-MECH-MODULE | PO Issued | 10 | 10 | 0 | 14067679 | 0 | 1406767.94 | 14067679.4
G | DTO-G | MCG | POINT EIGHT POWER | PEP-1.25MW CAT-SWITCHBOARD | PO Issued | 1 | 1 | 0 | 365950 | 0 | 365949.82 | 365949.82
G | DTO-G | SVL | AAON | AAON-RQA-011-DOAS | PO Issued | 2 | 2 | 0 | 133438 | 0 | 66718.75 | 133437.5
G | DTO-G | SVL | CONDAIR | CONDAIR-RS-030-HUMIDIFIER | PO Issued | 4 | 4 | 0 | 38843 | 0 | 9710.71 | 38842.84
G | DTO-G | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 2 | 2 | 0 | 145600 | 0 | 72800 | 145600
G | DTO-G | HYDRAQUIP | DANFOSS | DANFOSS-2" FD83-COUPLER | PO Issued | 1200 | 1200 | 0 | 631560 | 0 | 526.3 | 631560
G | DTO-G | T5 | CAT | CAT-1.25MW-GENERATOR | PO Issued | 2 | 2 | 0 | 1655365 | 0 | 827682.44 | 1655364.88
G | DTO-G | TEXAS AIR SYSTEMS | FISEN | FISEN-YVFA0459-CHILLED WATER PUMP SKID | PO Issued | 30 | 30 | 0 | 2413740 | 0 | 80458 | 2413740
G | DTO-G | TEXAS AIR SYSTEMS | WENDLAND | WENDLAND-30000 GAL HORIZONTAL-THERMAL STORAGE TANK | PO Issued | 4 | 4 | 0 | 1631796 | 0 | 407949 | 1631796
G | DTO-G | MCG | ABB | ABB-800A-STS | PO Issued | 72 | 72 | 0 | 7511868 | 0 | 104331.5 | 7511868
G-MMR | DTO-G-MMR | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 4 | 4 | 0 | 291200 | 0 | 72800 | 291200
H | DTO-H | CERIO | DELTA | DELTA-1250KVA-UPS | PO Issued | 42 | 42 | 0 | 14822260 | 0 | 352910.96 | 14822260.32
H | DTO-H | CERIO | DELTA | DELTA-250KVA-UPS | PO Issued | 30 | 30 | 0 | 3570304 | 0 | 119010.13 | 3570303.9
H | DTO-H | CERIO | DELTA | DELTA-600A-BUSWAY | PO Issued | 58 | 58 | 0 | 4442814 | 0 | 76600.24 | 4442813.92
H | DTO-H | CERIO | DELTA | DELTA-400A-BUSWAY | PO Issued | 2 | 2 | 0 | 153200 | 0 | 76600.24 | 153200.48
H | DTO-H | CERIO | DELTA | DELTA-800A-BUSWAY | PO Issued | 54 | 54 | 0 | 4136413 | 0 | 76600.24 | 4136412.96
H | DTO-H | CERIO | DELTA | DELTA-800A-STS | PO Issued | 54 | 54 | 0 | 5003100 | 0 | 92650 | 5003100
H | DTO-H | CERIO | DELTA | DELTA-63A-PIU | PO Issued | 54 | 54 | 0 | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY | INCLUDED IN BUSWAY
H | DTO-H | EAE | EAE | EAE-4000A-RESERVE BUSDUCT | PO Issued | 1114 | 1114 | 0 | 1038248 | 0 | 932 | 1038248
H | DTO-H | EAE | EAE | EAE-800A-RESERVE BUSDUCT TAP BOX | PO Issued | 72 | 72 | 0 | INCLUDED IN RBUS | INCLUDED IN RBUS | INCLUDED IN RBUS
H | DTO-H | JCI | JCI | JCI-500T-115-CHILLER | PO Issued | 30 | 30 | 0 | 17500846 | 0 | 583361.53 | 17500845.9
H | DTO-H | JCI | JCI | JCI-72K-FAN WALL | PO Issued | 48 | 48 | 0 | 5462916 | 0 | 113810.76 | 5462916.48
H | DTO-H | HYDRAQUIP | DANFOSS | DANFOSS-2" FD83-COUPLER | PO Issued | 1200 | 1200 | 0 | 631560 | 0 | 526.3 | 631560
H | DTO-H | JCL ENERGY | JCL ENERGY | JCL ENERGY-2550KVA 34.5KV KNAN-TRANSFORMER | PO Issued | 21 | 21 | 0 | 440880 | 0 | 20994.28 | 440879.88
H | DTO-H | JCL ENERGY | JCL ENERGY | JCL ENERGY-2550KVA 34.5KV KNAF-TRANSFORMER | PO Issued | 10 | 10 | 0 | 209943 | 0 | 20994.28 | 209942.8
H | DTO-H | MCG | MCFI | MCFI-IT-MODULE | PO Issued | 21 | 21 | 0 | 29542127 | 0 | 1406767.94 | 29542126.74
H | DTO-H | MCG | MCFI | MCFI-MECH-MODULE | PO Issued | 10 | 10 | 0 | 14067679 | 0 | 1406767.94 | 14067679.4
H | DTO-H | MCG | POINT EIGHT POWER | PEP-1.25MW CAT-SWITCHBOARD | PO Issued | 9 | 9 | 0 | 3293548 | 0 | 365949.82 | 3293548.38
H | DTO-H | SVL | AAON | AAON-RQA-011-DOAS | PO Issued | 2 | 2 | 0 | 133438 | 0 | 66718.75 | 133437.5
H | DTO-H | SVL | CONDAIR | CONDAIR-RS-030-HUMIDIFIER | PO Issued | 4 | 4 | 0 | 38843 | 0 | 9710.71 | 38842.84
H | DTO-H | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 2 | 2 | 0 | 145600 | 0 | 72800 | 145600
H | DTO-H | T5 | CAT | CAT-1.25MW-GENERATOR | PO Issued | 18 | 18 | 0 | 14898284 | 0 | 827682.44 | 14898283.92
H | DTO-H | TEXAS AIR SYSTEMS | FISEN | FISEN-YVFA0459-CHILLED WATER PUMP SKID | PO Issued | 30 | 30 | 0 | 2413740 | 0 | 80458 | 2413740
H | DTO-H | TEXAS AIR SYSTEMS | WENDLAND | WENDLAND-30000 GAL HORIZONTAL-THERMAL STORAGE TANK | PO Issued | 4 | 4 | 0 | 1631796 | 0 | 407949 | 1631796
H-MMR | DTO-H-MMR | SVL | DADEX | DADEX-60KW-CRAH | PO Issued | 4 | 4 | 0 | 291200 | 0 | 72800 | 291200
| Total | [7 empty] | 123868739 | 0 |  | 123868739.42